## Audit To-Dos
AureonCare — Security Audit To-Do Register
Audit performed 2026-08-01 on branch claude/security-audit-impact-vEc4g. Status updated 2026-09-09. ALL 26 findings fixed in code. Remaining work is deployment and verification only: run migrations 063-074 + tenant fan-out, switch AC_DB_U to aureoncare_app, set AC_IDX_K / AC_PLAT_S / AC_MSG_KEY / AC_RD_H, register the Microsoft Web redirect URI, test both OAuth providers, then set AC_DISABLE_LEGACY_SOCIAL_TOKEN=true.
ID | Severity | Area / Module | Finding | Location (file:line) | Root Cause | Recommended To-Do (fix) | Impacted Modules — linked changes to plan | Effort | Priority | Status (fix ref)
SEC-01 | Critical | Users / RBAC | Any authenticated non-admin can escalate to admin by sending role:'admin' when editing their own record. | backend/routes/users.js:222,263 | PUT /:id uses isSelfOrAdmin but the handler applies role = COALESCE($3, role) from req.body with no admin-only guard on the role field. | Whitelist self-editable fields; only allow role/status changes when req.user.role === 'admin'. | users.js; middleware/auth.js (authorize); user_roles sync (lines 301-360); frontend profile-edit form. | S | P0 | ✔ Fixed — 5414409
SEC-02 | Critical | Patient Portal | Unauthenticated POST /patient-portal/register enables the portal and sets a password for ANY patientId. | backend/routes/patient-portal.js (register handler) | Route has no authenticate/session guard and no :patientId in its path, so router.param session check never runs. | Require staff JWT or an authenticated portal session that owns the patientId before enabling portal / setting password. | patient-portal.js; middleware/auth.js; staff 'enable portal' flow; frontend portal-enable UI. | S | P0 | ✔ Fixed — 5414409
SEC-03 | Critical | Patient Portal / Social | Portal social login issues a 24h session on provider+providerId match without validating the access token. | backend/routes/patient-portal.js:91-109 | accessToken is destructured but never passed to validateSocialToken; a non-secret provider user-id is treated as a credential. | Call validateSocialToken(provider, accessToken) and match the provider-verified id before issuing a session (mirror auth.js). | utils/socialTokenValidator.js; routes/auth.js (parity); frontend portal social-login. | S | P0 | ✔ Fixed — 5414409
SEC-04 | Critical | Password Reset | forgot-password returns the reset token in the API response and the modal renders it, so anyone can reset any account by email alone. | backend/routes/auth.js:158-172; frontend ForgotPasswordModal.js:59,160; apiService.js:567 | Reset token delivered to the client instead of emailed out-of-band to the account owner. | Email the token server-side; never return it in the response. Client only collects the token the user received. | auth.js (forgot/reset-password); email/notification service (SendGrid); ForgotPasswordModal.js; apiService.forgotPassword. | M | P0 | ✔ Fixed — 5414409 + 3c9cfa0
SEC-05 | High | Multi-tenancy / PHI | No tenant isolation: no route scopes queries by clinic/org, so any authenticated user can read every clinic's patients & PHI. | backend/routes/*.js (no clinic_id/org_id references found) | Queries filter by record id only, never by an owning clinic/org tied to req.user. | Introduce clinic/org scoping (column + WHERE clause) on all PHI tables & queries, derived from req.user. Confirm whether product is multi-tenant. ¦ PLAN: SEC-05_MULTI_TENANCY_PLAN.md — recommend Model D (schema-per-tenant + control plane) for isolation with release-safe config/data; alternatives A (silo) / C (pool+RLS). | ALL PHI routes (patients, appointments, claims, medical-records, prescriptions, lab-orders, diagnosis, payments); DB schema/migrations; auth middleware to attach clinic_id; reporting/FHIR/EDI exports. | XL | P1 | ✔ Fixed (implemented) — Model D schema-per-tenant delivered: control plane, 78-table cutover, full route sweep, identity scoping by practice_id, hardened portal routing, least-privilege DB role, cross-tenant tests + CI guard. Remaining: deploy migrations 063-074 and set AC_DB_U/AC_IDX_K.
SEC-06 | High | Frontend / API | Most PHI-bearing frontend calls use bare fetch() with no Authorization header (only users/providers/inventory send a token). | frontend/src/api/apiService.js (patients, appointments, claims, payments, medical-records, prescriptions, diagnosis, FHIR) | Token attachment was retrofitted onto only a few methods; the rest call anonymously. | Route every method through authenticatedFetch; verify each backend route now rejects tokenless calls (post Fix #2). | apiService.js (all methods); every view/form calling api.*; backend route middleware (regression-test Fix #2). | M | P1 | ✔ Fixed — 2a78980
SEC-07 | High | Auth / Social | Social login auto-links to an existing password account by matching email without checking provider email_verified. | backend/routes/auth.js:256,304-328; utils/socialTokenValidator.js:36-43 | validateSocialToken returns email without asserting the provider marked it verified. | Only match/link by email when the provider reports it verified; otherwise require explicit authenticated linking. | socialTokenValidator.js (surface emailVerified); auth.js social-login/social-register; patient-portal linking. | M | P1 | ✔ Fixed — 2a78980
SEC-08 | High | Auth / Social linking | link-social-account (and portal link-social) links a client-supplied providerId to an account with no token validation. | backend/routes/auth.js:566-607; patient-portal.js:539-573 | Endpoint trusts a client-claimed providerId, letting a user claim someone else's social identity. | Validate accessToken with the provider and store only the verified canonical id; bind to the session user/patient. | socialTokenValidator.js; auth.js; patient-portal.js; social_auth schema (user_id consistency). | M | P1 | ✔ Fixed — 2a78980
SEC-09 | Medium | Auth / JWT lifecycle | Stateless JWTs (24h) are never revoked on password change or logout; a stolen/old token keeps working. | backend/middleware/auth.js:14-19; routes/auth.js:88-134 | No token_version/password_changed_at check in authenticate and no revocation list. | Add token_version (or password_changed_at) claim checked against DB in authenticate; bump on password change/reset/logout. | middleware/auth.js (authenticate, signToken); auth.js (change/reset-password, new logout); users schema; SEC-16/18 depend on this. | M | P2 | ✔ Fixed — e4038cb
SEC-10 | Medium | Auth / Config | JWT secret read from AC_TK_S with only a console.warn if missing and no strength check — weak/absent secret possible in prod. | backend/middleware/auth.js:3-8 | No fail-fast startup validation on secret presence/entropy. | Throw on startup if secret unset or < 32 bytes. | middleware/auth.js; server bootstrap/config; deployment env management. | S | P2 | ✔ Fixed — e4038cb
SEC-11 | Medium | Auth / JWT | jwt.verify called without an algorithms allowlist (no explicit defense vs algorithm confusion). | backend/middleware/auth.js:36,103,149 | Relies on library defaults instead of pinning algorithms:['HS256']. | Pass { algorithms: ['HS256'] } to every jwt.verify call. | middleware/auth.js only (authenticate, optionalAuth, requireAdmin). | S | P2 | ✔ Fixed — e4038cb
SEC-12 | Medium | Password policy | Minimum password length is 6 with no complexity; bcrypt cost factor 10 across the app. | backend/routes/auth.js:98-99,188-189; patient-portal.js:165 | Weak validation constants and low-for-healthcare bcrypt work factor. | Enforce >=12 chars + complexity/breach check; raise bcrypt cost to >=12. | auth.js (change/reset-password); patient-portal.js (register); user-creation route; frontend validation. | M | P2 | ✔ Fixed — ca06b7f — breach/HIBP check deferred
SEC-13 | Medium | Frontend / XSS | dangerouslySetInnerHTML renders parseMarkdown() output that does not escape HTML, injecting raw markup (incl. user chat input). | frontend EnhancedAIAssistant.js:20-30,256; HelpDrawer.js:12-22,265 | Hand-rolled markdown converter emits HTML without entity-escaping the source. | HTML-escape input before formatting and/or sanitize with DOMPurify; or render as plain text. | EnhancedAIAssistant.js; HelpDrawer.js; any component reusing parseMarkdown; add DOMPurify dependency. | S | P2 | ✔ Fixed — ca06b7f
SEC-14 | Medium | Frontend / PHI logging | Extensive console.log of patient records, appointments, prescriptions and IDs is shipped in the client. | frontend PatientPortalView.js:135,267,573; ViewEditModal.js:2164; ePrescribeModal.js | Debug PHI logging never stripped for production. | Remove PHI logging; gate diagnostics behind a dev flag or strip logs at build time. | PatientPortalView.js; ViewEditModal.js; ePrescribeModal.js; apiService.js; AppContext.js; build config. | S | P2 | ✔ Fixed — ca06b7f
SEC-15 | Medium | Frontend / Token storage | JWT, portalSessionToken and the full user/patient (PHI) object are stored in sessionStorage — stealable via XSS. | frontend apiService.js:13,739; context/AppContext.js:54,81 | Bearer tokens & PHI persisted in JS-accessible web storage. | Move session tokens to HttpOnly/Secure/SameSite cookies; store only a minimal non-PHI id client-side and re-fetch profile. | apiService.js; LoginPage.js; PatientLoginPage.js; AppContext.js; backend cookie + CSRF (new); couples with SEC-13. | L | P2 | ✔ Fixed — HttpOnly session cookie + CSRF double-submit; PHI no longer persisted client-side; API now same-origin (relative /api) so the cookie is first-party (SameSite=Lax) and the JWT is no longer stored in sessionStorage at all.
SEC-16 | Medium | Session / Logout | Logout only clears local state; no backend revocation, and patientPortalLogout() is never called. | frontend App.js:782-792; apiService.js:816-824 | Logout is a purely client-side state reset. | Add backend logout/revocation for clinician + portal sessions and invalidate server-side on logout. | App.js; apiService.js; backend new /auth/logout + portal logout wiring; depends on SEC-09 token_version. | M | P2 | ✔ Fixed — e4038cb
SEC-17 | Low | Auth / Enumeration | User enumeration via timing (bcrypt skipped for unknown email) and distinct portal messages. | backend/routes/auth.js:44-69; patient-portal.js:119-131 | No dummy-hash compare for missing users; non-uniform error responses. | Always run a constant-time compare vs a dummy hash; return one generic error for all failures. | auth.js login; patient-portal.js login; frontend error handling copy. | S | P3 | ✔ Fixed — ca06b7f
SEC-18 | Low | Auth / Reset | Successful password reset does not revoke existing JWTs or portal sessions. | backend/routes/auth.js:194-214 | Reset updates only the password hash (ties to SEC-09). | Bump token_version and delete patient_portal_sessions rows on reset. | middleware/auth.js; auth.js reset-password; patient_portal_sessions table. | S | P3 | ✔ Fixed — e4038cb
SEC-19 | Low | Auth / Social id match | Social lookup matches on the client-supplied providerId OR the verified id; stricter isProviderIdMatch helper is imported but unused. | backend/routes/auth.js:265-270,466-469; socialTokenValidator.js:107-113 | MSAL homeAccountId migration accepts an unverified client id as a query key. | Match only on the provider-verified canonical id; migrate legacy rows instead of trusting the client id. | socialTokenValidator.js; auth.js social-login/register; social_auth data migration. | M | P3 | ✔ Fixed — edd66af (canonical-id match) + 03c7c8a (verified-email re-link keeps existing OAuth users working)
SEC-20 | Low | OAuth flow | Implicit browser OAuth: provider access_token handled in SPA JS and forwarded as a login credential (XSS-exfiltratable). | frontend LoginPage.js:51-67; PatientLoginPage.js:65-79 | OAuth done implicitly in the browser with the raw access token passed through JS. | Adopt authorization-code (server-side exchange) flow so provider tokens aren't in browser JS. | LoginPage.js; PatientLoginPage.js; apiService social methods; backend OAuth handler (new). | L | P3 | ✔ Fixed — Google and Microsoft use server-side authorization-code exchange on BOTH staff and patient-portal login; no provider token reaches browser JS. Verify both providers, then set AC_DISABLE_LEGACY_SOCIAL_TOKEN=true to retire the old endpoint.
SEC-21 | Info | Infra / Rate limiting | In-memory rate-limit store (Fix #10/#24) is not shared across Vercel serverless instances — effective limits are per-instance. | backend/middleware/rateLimiters.js; routes/patient-portal.js | Default MemoryStore doesn't persist across isolated serverless instances. | Back limiters with Redis (rate-limit-redis) using the Redis config already stubbed in server.js. | rateLimiters.js; patient-portal.js limiters; server.js Redis wiring; infra/env (Redis URL). | M | P3 | ✔ Fixed — limiters (auth, api, portal-ip, portal-account, platform-login) now use a Redis-backed shared store when AC_RD_H/AC_RD_URL is set, so limits are global rather than per serverless instance. Fails open on Redis outage; warns when unconfigured.
SEC-22 | Medium | SSRF / Integrations | Operator-supplied base_url used as an outbound endpoint with credentials attached; endpoints not admin-gated. | routes/vendorIntegrationSettings.js; services/vendorIntegrations/* | No URL validation and no role check on the settings write/test endpoints. | Validate against a public-address allowlist; restrict to admin. | vendorIntegrationSettings.js; utils/safeUrl.js; integrationOAuth getBaseUrl | M | P2 | ✔ Fixed — utils/safeUrl.js (https-only, no credentials, public-unicast only) applied on write and at use; both endpoints authorize(admin); getBaseUrl host-header hardened. calendar-sync/backupProviders/campaigns verified clean.
SEC-23 | Low | EDI / XML parsing | Potential XXE in EDI/XML handling flagged for review. | utils/edi835Parser.js; utils/edi837Generator.js; services/vendorIntegrations/surescriptsService.js | Audit could not confirm whether an XML parser resolved external entities. | Confirm no external-entity resolution; keep parsers builder-only. | EDI utils; surescriptsService | S | P3 | ✔ Assessed — NOT vulnerable. xml2js is used only as a Builder (no parse sink anywhere); EDI 835/837 are X12 text parsers, not XML. No XXE exposure. Parser robustness/fuzzing not assessed.
SEC-24 | Medium | Notifications / Abuse | No send-abuse throttling on notification/SMS/email paths — platform can be used as a relay or to spam a patient. | routes/notifications.js; services/notificationService.js | Only the global /api limiter applies; no per-recipient or per-endpoint send limit. | Add per-user/per-recipient send quotas and a dedicated limiter. | notifications.js; notificationService.js; rateLimiters.js | M | P2 | ✔ Fixed — per-RECIPIENT send quotas enforced in the sending layer (utils/sendQuota.js), so every trigger path is covered: email 20/h and WhatsApp 10/h by default (AC_SEND_MAX_*). Redis-shared across instances when configured; fails open so a password reset is never blocked.
SEC-25 | High | Audit / HIPAA | PHI reads are not audit-logged, and the per-tenant audit_logs table is mutable by the application. | routes/patients.js; routes/medical-records.js; tenant audit_logs | No audit instrumentation on read paths; no append-only constraint on tenant audit log. | Instrument PHI reads; make tenant audit_logs append-only as control.audit_log already is. | PHI read routes; audit middleware; tenant migration | M | P1 | ✔ Fixed — tenant audit_logs is append-only (tenant migration 002; UPDATE/DELETE rejected), and PHI reads on patients, medical-records, prescriptions, lab-orders and diagnosis are now logged via auditPhiRead + services/phiAudit. Audit writes survive an invalid patient FK so a read is never left unlogged.
SEC-26 | High | Backup / Encryption | PHI backups/archives are sent to third-party storage (Google Drive / OneDrive) without application-level encryption. | services/cloudBackupStorage.js; services/archiveScheduler.js | No encryption applied before upload; relies solely on the provider. | Encrypt PHI archives at rest before upload (AES-GCM with AC_EK), document key management. | cloudBackupStorage.js; archiveScheduler.js; backup routes | M | P1 | ✔ Fixed — backups sealed with AES-256-GCM (utils/backupCrypto.js) before upload; restore unseals and still accepts legacy plaintext archives. Verified: no plaintext PHI in the uploaded file, tampering rejected. Requires AC_MSG_KEY escrowed separately from the backups.

## Module Impact Map
Module Impact Map — plan linked changes by shared module
Each row is a code area multiple findings touch. Fix findings sharing a module together to avoid repeated regression testing and merge churn. Sequence P0>P1>P2>P3 within each module.
Module / File | Findings that touch it | Coordination note | Suggested sequencing
middleware/auth.js | SEC-09, SEC-10, SEC-11, SEC-18, (SEC-16) | Central auth choke point. token_version (SEC-09) unlocks SEC-16 & SEC-18; do algorithms allowlist (SEC-11) and secret validation (SEC-10) in the same pass. | SEC-11 + SEC-10 first (quick) -> SEC-09 (schema+claim) -> SEC-16, SEC-18.
routes/auth.js | SEC-04, SEC-07, SEC-08, SEC-09, SEC-12, SEC-17, SEC-18, SEC-19 | Highest-churn file. Reset-token (SEC-04) & invalidation (SEC-18) share reset/change handlers; social fixes share social-login/register handlers. | SEC-04 (P0) -> social cluster SEC-07/08/19 -> SEC-12/17 -> SEC-18.
routes/patient-portal.js | SEC-02, SEC-03, SEC-08, SEC-12, SEC-17, SEC-21 | SEC-02 (auth guard) and SEC-03 (token validation) are both P0 and edit adjacent handlers — do together. | SEC-02 + SEC-03 together (P0) -> SEC-08 -> SEC-12/17 -> SEC-21 Redis.
utils/socialTokenValidator.js | SEC-03, SEC-07, SEC-08, SEC-19 | Shared validator for all social flows. Surface emailVerified + strict id match once; every social finding consumes it. | Extend validator first, then update the 4 call sites.
DB schema / migrations | SEC-05, SEC-09, SEC-08 (user_id) | Schema changes: clinic/org column (SEC-05, large), token_version/password_changed_at (SEC-09), social_auth user_id (SEC-08). | Bundle into one migration set; SEC-05 scoped separately.
frontend/api/apiService.js | SEC-04, SEC-06, SEC-14, SEC-15, SEC-16 | All network + token handling. authenticatedFetch rollout (SEC-06) touches every method; cookie migration (SEC-15) rewrites token handling. | SEC-06 -> SEC-04 client bits -> SEC-16 -> SEC-15 (largest).
frontend/context/AppContext.js | SEC-15, SEC-14, SEC-04 | Auth/session state + storage. Cookie migration (SEC-15) and removing PHI from storage change init/persist effects. | Do alongside apiService SEC-15.
Email / notification service | SEC-04 | Reset-token emailing needs a working transactional email path (SendGrid TODO in auth.js:168). | Prereq for SEC-04 backend fix; may need infra/secret provisioning.
ALL PHI routes | SEC-05, SEC-06 | Tenant scoping (SEC-05) is cross-cutting across every PHI route; coordinate with frontend auth rollout (SEC-06). | Design tenancy model first; implement route-by-route behind tests.
Frontend help components | SEC-13 | parseMarkdown XSS isolated to EnhancedAIAssistant.js + HelpDrawer.js; add DOMPurify. | Standalone; ship independently.

## Already Fixed (context)
Already remediated on this branch (for reviewer context)
Fixed earlier in the security-audit branch; listed so planners don't re-open them. Re-verify after deploy.
Ref | Issue | Fix shipped | Regression check
Fix #2 | 38 route files had no authentication | router.use(authenticate) added to all; /uploads gated | Tokenless GET /api/* -> 401
Fix #6 | Portal /:patientId/* accepted arbitrary patientId (IDOR) | router.param session-to-patient binding (403 on mismatch) | Patient A token vs Patient B id -> 403
Fix #15 | Portal session tokens stored unhashed | SHA-256 hash at rest; raw token only on client | Stolen hash replay -> 401
Fix #24 | Portal login had no rate limit/lockout | Per-IP (20) + per-account lockout (3 failed/15m) | 4th bad attempt -> 429
Fix #10 | No rate limiting on any endpoint | Global apiLimiter (/api) + strict authLimiter (/api/auth) | 11th auth attempt -> 429

## Legend & Method
Legend, Scope & Method
Severity
Critical | Directly exploitable now; account takeover, privilege escalation, or mass PHI exposure. Fix immediately (P0).
High | Serious exposure needing a modest precondition, or a broad architectural gap. Plan next (P1).
Medium | Real weakness, harder to exploit or needs chaining. Scheduled hardening (P2).
Low | Defense-in-depth / best-practice gap. Backlog (P3).
Info | Operational/infra note, not a direct vuln.
Effort | S = <0.5 day ¦ M = 0.5-2 days ¦ L = 3-5 days ¦ XL = multi-week / cross-cutting.
Priority | P0 immediate ¦ P1 this sprint ¦ P2 next sprint ¦ P3 backlog.
Scope covered | Backend routes & middleware, auth/JWT/session/crypto, social login, frontend token/PHI handling & XSS, secrets/config, rate limiting, uploads, tenant isolation.
Positives found | No hardcoded secrets (env placeholders only); forgot-password backend uses 32-byte CSPRNG + 1h expiry + generic response; requireAdmin re-fetches role from DB; portal tokens CSPRNG; uploads have fileFilter + 10MB limit; no eval() in frontend.
Needs deeper review (agents hit session limit) | SSRF in calendar-sync / integrationOAuth / backupProviders / campaigns outbound calls; EDI/XML parsing (XXE); notification/SMS/email send-abuse throttling; audit-log write coverage on PHI reads & audit-log integrity; backup/archive PHI encryption at rest. Recommend a focused follow-up pass.
Method | 6 parallel read-only agents by vuln class + direct verification of key findings. No files modified. Line numbers current at audit time; re-anchor before editing.