## Read me
AureonCare video library — production tracker
What this is | A tracker for the 32 single-feature training videos planned in docs/demo/VIDEO_LIBRARY_PLAN.md, plus 6 backlog ideas and the one prep task that precedes them. Each video runs 1-2 minutes and covers one module feature end to end.
Status today | Plan only. Nothing has been produced yet. The Google Meet recording in docs/google-verification/ exists for Google's OAuth review and can be re-edited into video V26.
Sheets | Video Tracker — the working list, one row per video. Dashboard — counts and completion, all formula-driven. Lists — dropdown values; edit here to change the options.
How to use it | Fill in the yellow columns only: Owner, Status, the four stage columns, the three dates, Video URL and Notes. Everything else is reference data from the plan, and Progress / Days to target are formulas — do not overwrite them.
Progress | Counts how many of Script / Recorded / Edited / Reviewed are set to Yes, out of four.
Days to target | Target publish minus today. Blank once Actual publish is filled in. Negative and unpublished turns red.
Status meanings | Not started · Scripting (writing the beat sheet) · Recording (driving the app) · Editing (captions, titles, mp4) · In review (SME check) · Approved (SME signed off, not yet posted) · Published (live to viewers) · On hold
Example row | V03 ¦ Wave 1 ¦ P0 ¦ Book an appointment ¦ Scheduling ▸ Calendar ¦ Front desk ¦ 2 ¦ ... ¦ Owner: Product marketing ¦ Status: Editing ¦ Script Yes ¦ Recorded Yes ¦ Edited In progress ¦ Reviewed No ¦ Progress 50% ¦ Start 2026-08-10 ¦ Target 2026-08-24 ¦ URL blank until published
Conventions | 1280x720, no audio in v1 (captions carry the teaching), 5s title card + 10s why-this-matters + 60-90s journey + 10s recap. Synthetic data only, with the demo-environment watermark. Personas from docs/demo/DEMO_SCENARIOS.md.
Re-cut trigger | Any change to the app shell, a module's tab layout, or a journey's step order invalidates the affected video. Keep every video script-driven so a re-cut is cheap.

## Dashboard
Dashboard — recalculates from the Video Tracker
Overall
Items tracked | 39
Videos planned | 38
Published | 0
In flight (started, not published) | 10
Not started | 29
Overall completion | 19.23%
Planned runtime (min) | 73.4
Published runtime (min) | 0
By wave
Wave | Videos | Published | Complete | Runtime (min)
Prep | 1 | 0 | 75% | 0
Wave 1 | 8 | 0 | 75% | 13.5
Wave 2 | 8 | 0 | 9.375% | 20.4
Wave 3 | 7 | 0 | 0% | 13
Wave 4 | 9 | 0 | 0% | 17
Backlog | 6 | 0 | 0% | 9.5
By status
Status | Count | Share
Not started | 29 | 74.36%
Scripting | 0 | 0%
Recording | 0 | 0%
Editing | 0 | 0%
In review | 10 | 25.64%
Approved | 0 | 0%
Published | 0 | 0%
On hold | 0 | 0%
By stage
Stage | Done | In progress | Not started
Scripts | 10 | 0 | 29
Recordings | 10 | 0 | 29
Edits | 10 | 0 | 29
Reviews | 0 | 0 | 39
Every figure here is a formula over the Video Tracker sheet — update the tracker, not this sheet.

## Lists
Status | Yes / No | Wave | Priority | Owner | Edit these lists to change the dropdown options on the Video Tracker.
Not started | No | Prep | P0 | Unassigned
Scripting | In progress | Wave 1 | P1 | Product marketing
Recording | Yes | Wave 2 | P2 | Clinical SME
Editing |  | Wave 3 | P3 | Billing SME
In review |  | Wave 4 | P4 | Video editor
Approved |  | Backlog |  | Engineering
Published
On hold

## Video Tracker
Video Tracker — one row per video · fill in the yellow columns only
ID | Wave | Priority | Title | Module / path in app | Audience | Target (min) | Journey (end to end) | What it teaches | Owner | Status | Script | Recorded | Edited | Reviewed | Progress | Start date | Target publish | Actual publish | Days to target | Video URL | Notes
P01 | Prep | P0 | Shared recorder harness | docs/google-verification/record-google-meet-demo.js | Production |  | Generalise the Google Meet recorder: shared fixtures, caption bar, title cards, cursor, mp4 output; one script per video. | One-time cost that makes all 32 videos re-cuttable when the UI changes. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Harness at docs/demo/video-harness — branding kit and narration pipeline included.
V01 | Wave 1 | P0 | Find your way around AureonCare | App shell · search · help | Everyone | 1.5 | Sign in → three-pane shell → switch workspaces → universal search jumps to a patient → help drawer → AI assistant → theme and language switch. | The navigation model, so every later video can say 'go to X ▸ Y'. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Recorded, branded (logo bumper, caption-bar mark, outro) and narrated. Voice is placeholder TTS — re-render with VOICE_ENGINE=files before publishing.
V02 | Wave 1 | P0 | Register a new patient | Patients ▸ Patient Records | Front desk | 1.5 | New Patient → demographics, contact, insurance, emergency contact → save → record opens → set status → invite to portal. | Which fields matter downstream: insurance drives claims, email drives the portal. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Recorded, branded (logo bumper, caption-bar mark, outro) and narrated. Voice is placeholder TTS — re-render with VOICE_ENGINE=files before publishing.
V03 | Wave 1 | P0 | Book an appointment | Scheduling ▸ Calendar | Front desk | 2 | Day/week/month views → pick a slot → New Appointment (patient, provider, type, duration, telehealth) → save → reschedule → cancel with reason → reminders. | Appointment type drives duration, and cancelling is not deleting. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Recorded, branded (logo bumper, caption-bar mark, outro) and narrated. Voice is placeholder TTS — re-render with VOICE_ENGINE=files before publishing.
V04 | Wave 1 | P0 | Read your day on the dashboard | Home ▸ Dashboard | Everyone | 1 | Metric tiles and what each counts → appointments quick view → tasks quick view → revenue quick view → click through to the module. | The dashboard is a launchpad, not a report. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Recorded, branded (logo bumper, caption-bar mark, outro) and narrated. Voice is placeholder TTS — re-render with VOICE_ENGINE=files before publishing.
V05 | Wave 1 | P0 | Document a visit | Patients ▸ Patient Records | Clinician | 2 | Open the chart → history timeline → new clinical record → chief complaint and notes → vitals → allergies → save → appears on timeline and in portal. | The chart is the single source of truth, and the patient sees what you save. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Recorded, branded (logo bumper, caption-bar mark, outro) and narrated. Voice is placeholder TTS — re-render with VOICE_ENGINE=files before publishing.
V06 | Wave 1 | P0 | Run a telehealth visit | Clinical ▸ Telehealth | Clinician | 2 | Active provider banner → New Session from an appointment → attach pre-session consent form → join link → Join → end → session under Recent. | Scheduled session vs Instant meeting; pre-session forms land in the portal. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Recorded, branded (logo bumper, caption-bar mark, outro) and narrated. Voice is placeholder TTS — re-render with VOICE_ENGINE=files before publishing.
V07 | Wave 1 | P0 | Create and submit a claim | Billing ▸ Claims | Billing | 2 | New Claim from a completed encounter → payer, codes, charges → save draft → validate → submit to clearinghouse → status Submitted → where rejections surface. | The claim states and what each one means for cash. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Recorded, branded (logo bumper, caption-bar mark, outro) and narrated. Voice is placeholder TTS — re-render with VOICE_ENGINE=files before publishing.
V08 | Wave 1 | P0 | What your patients see | Patients ▸ Patient Portal | Front desk · clinician | 1.5 | Portal as the patient: overview → appointments → diagnoses → prescriptions → records → forms requested → complete a form → submission appears staff-side. | Staff can answer portal questions, and know what publishing exposes. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-01 |  |  |  |  | Recorded, branded (logo bumper, caption-bar mark, outro) and narrated. Voice is placeholder TTS — re-render with VOICE_ENGINE=files before publishing.
V09 | Wave 2 | P1 | Get a pre-authorization approved | Billing ▸ Pre-Authorizations | Billing | 2.5 | New pre-auth against payer and service → clinical justification → submit → track Submitted → Approved/Denied → link to appointment and claim. | Do this before the visit, not after the denial. | Unassigned | Not started | No | No | No | No | 0% | [5 empty] | Re-rendered against the merged UI.
V10 | Wave 2 | P1 | Work a denial to resolution | Billing ▸ Denials | Billing | 2.7 | Denials queue → open a denied claim → read the denial reason → correct the coding → resubmit → track the appeal. | The denial reason codes staff actually see, and the resubmit path. | Unassigned | Not started | No | No | No | No | 0% | [5 empty] | Re-rendered against the merged UI.
V11 | Wave 2 | P1 | Record a payment and post it | Billing ▸ Payments / Payment Postings | Billing | 2.9 | Record an insurance payment → allocate across claim lines → patient responsibility → balance updates on the claim and in Receivables. | Why unposted payments distort AR. | Unassigned | Not started | No | No | No | No | 0% | [5 empty] | Re-rendered against the merged UI.
V12 | Wave 2 | P1 | Quote, invoice, get paid | Billing ▸ Quotes & Invoices | Front desk · billing | 2.3 | Build a quote from the catalogue → convert to invoice → send → take a card payment via Stripe → receipt → invoice closes and Accounting reflects it. | The self-pay path, which the claims videos do not cover. | Unassigned | Not started | No | No | No | No | 0% | [5 empty] | Re-rendered against the merged UI.
V13 | Wave 2 | P1 | Prescribe and send electronically | Clinical ▸ Diagnoses ▸ e-Prescribe | Clinician | 2.4 | New prescription → drug, dose, refills → interaction and allergy check fires → choose the patient's pharmacy → send via Surescripts → status → appears in portal. | The safety checks are the point; do not click past them. | Unassigned | Not started | No | No | No | No | 0% | [5 empty] | Re-rendered against the merged UI.
V14 | Wave 2 | P1 | Order a lab and file the result | Clinical ▸ Laboratories | Clinician | 2.6 | New lab order → panel and diagnosis → transmit to Labcorp → track status → result returns → review, flag abnormal, file to chart → notify patient. | The ordering loop closes in the chart, not in email. | Unassigned | Not started | No | No | No | No | 0% | [5 empty] | Re-rendered against the merged UI.
V15 | Wave 2 | P1 | Record a diagnosis | Clinical ▸ Diagnoses | Clinician | 2.3 | New diagnosis → ICD-10 search → status (active/resolved/chronic) → onset → link to encounter → flows onto claims and the portal. | Diagnosis quality drives claim acceptance. | Product marketing | In review | Yes | Yes | Yes | No | 75% | 2026-08-12 |  |  |  |  | Re-recorded against the relocated nav (Clinical, not Patients) and the new patient picker on the standalone form. Narrated with google/en-US-Neural2-D to match the rest of the library. Re-rendered against the merged UI.
V16 | Wave 2 | P1 | Set up appointment types and provider schedules | Scheduling ▸ Setup / Providers | Admin | 2.7 | Appointment types with durations, colours, telehealth defaults → provider working hours → time off → calendar reflects both immediately. | Most scheduling complaints are a configuration problem, fixed here. | Unassigned | Not started | No | No | No | No | 0% | [5 empty] | Re-rendered against the merged UI.
V17 | Wave 3 | P2 | Let patients book themselves | Public booking page | Admin · front desk | 2 | Configure bookable types → share the public link → patient flow (Select Type → Choose Time → Your Info → Confirm) → booking lands on the calendar. | What patients can and cannot self-book. | Unassigned | Not started | No | No | No | No | 0%
V18 | Wave 3 | P2 | Fill a cancelled slot from the waitlist | Scheduling ▸ Waitlist | Front desk | 1.5 | Add a patient with priority and flexibility → a cancellation opens a slot → notify next patient → confirm → appointment created, entry clears. | The waitlist only works if entries carry real availability windows. | Unassigned | Not started | No | No | No | No | 0%
V19 | Wave 3 | P2 | Collect intake and consent before arrival | Patients ▸ Patient Intake | Front desk | 2 | Build an intake flow from forms → send to patient → patient completes in portal → staff review → data lands on chart → consent stored with timestamp. | Intake forms vs intake flows vs consent forms. | Unassigned | Not started | No | No | No | No | 0%
V20 | Wave 3 | P2 | Build a form template and read the submissions | Patients ▸ Form Templates | Admin | 2 | New template → field types and required fields → publish → assign to a patient → submissions tab → open a completed submission → form audit log. | Forms are versioned and audited; edit deliberately. | Unassigned | Not started | No | No | No | No | 0%
V21 | Wave 3 | P2 | Answer a question with a report | Insights ▸ Reports | Manager | 1.5 | Operational vs financial vs insurance categories → open No-Show Report → date range → chart type → read the trend → export to PDF/Excel. | Which report answers which question. | Unassigned | Not started | No | No | No | No | 0%
V22 | Wave 3 | P2 | Build a custom report and export it | Insights ▸ Custom Report | Manager | 2 | Custom Report → data source, columns, filters, grouping → preview → save → export. | The escape hatch when no standard report fits. | Unassigned | Not started | No | No | No | No | 0%
V23 | Wave 3 | P2 | Package services and run a promotion | Growth ▸ Service Catalog | Manager | 2 | Create a service with price and duration → bundle into a package → category → promotion with validity window → appears in booking and quotes → statistics. | Pricing lives in one place and flows everywhere. | Unassigned | Not started | No | No | No | No | 0%
V24 | Wave 4 | P3 | Configure your clinic | Settings ▸ Practice | Admin | 2 | Clinic identity, address, timezone, currency → working hours → appointment rules (slot length, buffers, booking window). | These settings are upstream of scheduling behaviour. | Unassigned | Not started | No | No | No | No | 0%
V25 | Wave 4 | P3 | Add users and control what they can see | Settings ▸ Access Control | Admin | 2 | Invite a user → assign role → permissions matrix → module-level effect → multi-role users → plan gating vs role gating. | The two independent gates that explain 'why can't I see this module'. | Unassigned | Not started | No | No | No | No | 0%
V26 | Wave 4 | P3 | Connect a video provider | Settings ▸ Telehealth Setup | Admin | 1.5 | Telehealth Setup → connect an account via OAuth → test connection → enable → becomes the active provider in Telehealth. | Re-edit of the existing Google Meet recording — cheapest video in the list. | Unassigned | Not started | No | No | No | No | 0%
V27 | Wave 4 | P3 | Connect pharmacy, lab and payment partners | Settings ▸ Integrations | Admin | 2 | Integrations → Surescripts, Labcorp, Optum, Stripe → credentials → sandbox vs live → enable → where each shows up in daily work. | An integration must be configured before it can be enabled. | Unassigned | Not started | No | No | No | No | 0%
V28 | Wave 4 | P3 | Stock: item to purchase order to receipt | Operations ▸ Inventory | Ops | 2 | Create an item with category and reorder point → stock levels → low-stock alert → purchase order to supplier → receive stock → levels update. | The reorder point is what makes the alerts useful. | Unassigned | Not started | No | No | No | No | 0%
V29 | Wave 4 | P3 | Close the books | Operations ▸ Accounting | Finance | 2 | Chart of accounts → journal entries → receivables and payables ageing → reconciliation against a statement → generate statements. | How clinical and billing activity lands in the ledger. | Unassigned | Not started | No | No | No | No | 0%
V30 | Wave 4 | P3 | Prove who touched what | Settings ▸ Audit Logs | Compliance | 1.5 | Audit Logs → filter by user, patient, action, date → open an entry → export for an audit request. | The HIPAA answer to 'who viewed this record'. | Unassigned | Not started | No | No | No | No | 0%
V31 | Wave 4 | P3 | Back up, restore, archive | Settings ▸ Backup & Restore | Admin · IT | 2 | Run a backup → what it includes → restore preview → archive old records → retrieve from archive. | Archive and backup solve different problems. | Unassigned | Not started | No | No | No | No | 0%
V32 | Wave 4 | P3 | Exchange data over FHIR | Clinical ▸ FHIR Resources / Tracking | IT | 2 | Browse resource types → inspect a Patient/Observation resource → FHIR Tracking shows exchanges and failures → retry a failed exchange. | Where to look when a partner says 'we didn't get it'. | Unassigned | Not started | No | No | No | No | 0%
B01 | Backlog | P4 | Notifications and tasks | Cross-module | Everyone | 1.5 | Assign a task → recipient is notified → complete it → the loop closes on the dashboard. |  | Unassigned | Not started | No | No | No | No | 0%
B02 | Backlog | P4 | Merge duplicate patients | Patients ▸ Patient Records | Front desk | 1.5 | Identify duplicates → compare records → merge → verify history survived the merge. |  | Unassigned | Not started | No | No | No | No | 0%
B03 | Backlog | P4 | Patient history and health metric trends | Patients ▸ Patient History | Clinician | 1.5 | Open history → health metrics over time → chart a vital → spot a trend across visits. |  | Unassigned | Not started | No | No | No | No | 0%
B04 | Backlog | P4 | CRM and campaigns | Growth ▸ CRM | Manager | 2 | Lead capture → CRM pipeline → build a campaign → send → measure response. |  | Unassigned | Not started | No | No | No | No | 0%
B05 | Backlog | P4 | Working in another language | App shell | Everyone | 1.5 | Switch language (en/es/fr/de/ar) → translated UI → right-to-left layout in Arabic. |  | Unassigned | Not started | No | No | No | No | 0%
B06 | Backlog | P4 | Recurring appointments | Scheduling ▸ Calendar | Front desk | 1.5 | Create a recurring series → edit one occurrence vs the series → cancel the series. |  | Unassigned | Not started | No | No | No | No | 0%
Formulas:
Days to target = IF([Actual publish]<>"","",IF([Target publish]="","",[Target publish]-TODAY()))